## timetable
SAMPLE
Chapter Seminar Timetable
As of (Date)
Event | Event Date(s) |  | Key Staff
(Name) Chapter | Date(s) |  | Chapter Officer #1
Name of Hotel/Facility |  |  | Chapter Officer #2
Address
City, State/Province, Zip/Postal Code
Telephone/Fax
Direct Line to Sales/Convention Services
Hotel Sales Person/Hotel Convention Services
| Project Target | Completed | Completed
20 weeks prior | Date | Date | By
Identify topic/speaker | (date)
Identify type of facility/venue | (date)
Prepare budget/breakeven figures | (date)
Prepare timetable | (date)
Tentative outline speakers/programming | (date)
Contact hotels-prepare Request for Proposal (RFP) | (date)
Tentative Schedule of Events | (date)
Review of Logistics (attendance, meals, golf) | (date)
19 weeks prior
Select property | (date)
18 weeks prior
Negotiate and prepare hotel contract | (date)
16 weeks prior
Promote event via email; advise National for website listing | (date)
Prepare materials for brochure (program/hotel/rates/activities/cutoff dates/etc.) | (date)
Prepare mailing list | (date)
Confirm speakers/panelists/moderators; obtain bios | (date)
Final agenda with speakers for brochure | (date)
Draft confirmation letter for attendees | (date)
14 weeks prior
Promotional Brochure/flyer designed & printed | (date)
12 weeks prior
Mail first Brochure/flyer to attendees | (date)
Obtain speaker a/v needs, arrival times, sleeping room req | (date)
Ongoing after first mailing
Process registration forms and calls | ongoing
Send confirmation letters to registrants | ongoing
Review attendance weekly; assign follow-up calls | ongoing
Cross reference hotel list w/attendance list | ongoing
8 weeks prior
Mail second meeting announcement | (date)
Order badge stock | (date)
Order ribbons (if applicable) | (date)
Golf Awards (if applicable) | (date)
Speaker gifts (if applicable) | (date)
Officer/VIP/Guest gifts (if applicable) | (date)
6 weeks prior
E-Mail/Fax reminder | (date)
Make speaker/other hotel reservations | (date)
Review room pick-up with hotel; release rooms as approp.
Finalize master account information with Hotel
Speakers arrival/departures/Master account info to hotel | (date)
Define general A/V requirements | (date)
Prepare Meeting Specifications (menus, a/v, see form) | (date)
Select meeting room set-up (see diagrams) | (date)
4 weeks prior
Telephone calls to those not registered | (date)
Conference call speakers/panelists/moderators | (date)
Speakers a/v requirements | (date)
3 weeks prior
Determine if Signage required and order | (date)
Review BEOs (Banquet Event Orders) with hotel | (date)
2 weeks prior
Speaker handouts printed | (date)
Process check requests for speaker fees | (date)
Follow-up with hotel room, a/v, special diets | (date)
Table assigned seating (if applicable) | (date)
1 week prior
Final Program Schedule printed | (date)
Evaluation Forms printed | (date)
Announcement/Introductions to moderators | (date)
Shipment material to hotel (handouts, etc.) | (date)
Final Attendance List for distribution | (date)
Prepare badges | (date)
Note cards for gifts (if applicable) | (date)
48-72 hours prior
Review room list with hotel
Guarantees for all events to hotel | (date)
Day of Event
Meet on-site with presenters/hotel staff to review program | (date)
On-site checklist duties | (date)
1 week after
Thank you letters | (date)
Evaluation tabulation | (date)
30 days after (approximate)
Reconcile billing when received, submit payment | (date)